## Bug Report
ID | Title | Severity | Status | Steps to Reproduce | Expected Result | Actual Result | Notes
BUG-001 | Homepage testimonials show placeholder names (USER 1, USER 2) | Medium | Open | 1. Go to http://localhost:3000 2. Scroll to testimonials section | Real customer testimonials with actual names | Placeholder text USER 1 and USER 2 shown as reviewer names | Marketing issue - looks unfinished to visitors
BUG-002 | /pricing route shows blank page | Critical | Open | 1. Navigate to http://localhost:3000/pricing | Pricing page with plan comparison and details | Blank/empty page rendered - no route defined in React Router | Console warning: No routes matched location /pricing
BUG-003 | Navbar Pricing link does not scroll to pricing section | Medium | Open | 1. Go to http://localhost:3000 2. Click Pricing in navbar | Page scrolls to pricing/plans section | No scroll occurs - no #pricing section exists on homepage | Anchor #pricing linked but no matching section on page
BUG-004 | Payment page delivery details pre-filled with placeholder data | High | Open | 1. Log in as any user 2. Navigate to /payment | Fields show logged-in user email or are empty | Full Name: Rahul Sharma, Email: rahul@gmail.com (hardcoded test data) | Users may submit with wrong delivery email causing missed file delivery
BUG-005 | Success page shows Amount Paid undefined without payment context | High | Open | 1. Log in as any user 2. Navigate directly to /success without completing payment | Redirect to /payment or show appropriate error state | Renders with Amount Paid: undefined, empty Payment ID, Email delivery failed error | Missing guard: /success should validate payment session before rendering
BUG-006 | Download page accessible without payment verification | High | Open | 1. Log in as any user 2. Navigate directly to /download without paying | Redirect to /payment or show locked state requiring purchase | Full download page renders with resume preview and download buttons accessible | Potential revenue bypass - users may download without paying
BUG-007 | UPI payment app icons not rendering (show as gray circles) | Medium | Open | 1. Go to /payment 2. Select UPI tab 3. Observe payment app shortcuts | GPay, PhonePe, Paytm, BHIM logos visible as clickable shortcuts | All four icons appear as blank gray circles with no logo or branding | Images may have failed to load or are missing from asset bundle
BUG-008 | Sign out does not reset page scroll position | Low | Open | 1. Log in and scroll down on any page 2. Click Sign Out | Redirect to homepage with scroll position reset to top | Browser retains previous scroll position after sign out | Minor UX issue - not critical but can be disorienting
BUG-009 | Admin login email placeholder looks like a pre-filled value | Low | Open | 1. Navigate to /admin/login 2. Observe email field without clicking | Email field visually empty or clearly labeled as placeholder | Placeholder admin@resumate.ai visually indistinguishable from filled value | Can confuse admins into thinking field is pre-filled; error still triggers on empty submit